MMTO – MAESTRO Team Meeting.

10th May 2007, 11am – 1pm, Room 450.

| Attendees (MMTO): | Shawn Callahan, Tom Gerl, John Glaspey, Morag Hastie, Cory Knop, Ricardo Ortiz, Tim Pickering, Skip Schaller, Betty Stobie, Ken van Horn, Faith Vilas, Grant Williams, J.T. Williams. |
| --- | --- |
| Attendees (MAESTRO): | Jill Bechtold, David Dean, Mike Lesser, Michelle Reed, Russ Warner |
| Apologises | Dennis Smith, Jeff Rill |

Summary of Actions

|  | ON | ACTION | DATE | STATUS |
| --- | --- | --- | --- | --- |
| 1 | David D | Supply list of deliverable parts with weights of each to John G | Before ‘Delivery’ meeting | Open |
| 2 | David D | Supply John G with weight and COG estimates appropriate for both crane lifts and mounting on the telescope | Before 06/01/07 | Open |
| 3 | David D | Supply John G with dimensions of instrument enclosure. Most important is height of the enclosure as a function of distance from the rotator. | Before 06/11/07 | Open |
| 4 | David D & Jill B | Observe Hectochelle installation | 06/11/07 | Open |
| 5 | David D & Jill B | Look at the LGS storage tent in the pit | 06/11/07 | Open |
| 6 | Jill B | Discuss LGS storage tent with Matt Radmacher for material types etc - e-mail discussion started 05/11/07 | Before 07/01/07 | Open |
| 7 | Jill B | Develop check list for mounting MAESTRO | Review 06/11/07 | Open |
| 8 | John G, JT | Interior dimensions of the air ride truck for shipping (width x length x height). Also need to know height of door frame, height of back of the truck, distance from the mid of the rear wheel and the back of the track and the wheel base dimensions. | Before ‘Delivery’ meeting | Open |
| 9 | John G | Send Jill B a copy of the Hectochelle mounting check list - Jill B received documents and requested ‘Detailed Hectospec Fiber Positioner Installation and Removal Procedure’ - requested document e-mailed by Morag H |  | Closed |
| 10 | John G, Ricardo O, Jill B | Coordinate clearing the footprint for the required storage area in the pit and mark off with tape. | Before 07/18/07 | Open |
| 11 | John G | Integrate MAESTRO into the balancer GUI | Before mid June | Open |
| 12 | John G | Supply David D with dimensions of the new instrument lift | Before 06/01/07 | Open |
| 13 | John G | Organise a fork-lift truck suitable for removing the instrument & cart from truck at the summit | Before 07/18/07 | Open |
| 14 | John G | Consider and deal with any potential interference of MAESTRO with brackets etc around the rotator | Before 07/24/07 | Open |
| 15 | Mike L | Find solution for reducing chance of frosting of the window while moving the dewar cold and determine if window can safely frost up without damage. | Before 07/18/07 | Open |
| 16 | Mike L | Obtain new PCI card for MAESTRO | Before 07/18/07 | Open |
| 17 | Morag H | Arrange meeting to discuss loading instrument on the truck. Personnel: Russ W, Ricardo O, JT, John G, Bill S. - e-mail discussions started 05/14/07. | Before 06/01/07 | Open |
| 18 | Morag H | Schedule review of mounting procedure with involved personnel day before actual move at telescope. | Date of review: 07/24/07 | Open |
| 19 | Morag H | Arrange meeting to overview documentation status. Personnel: Jill B, Cory K, Morag H, Grant W | Post 07/28/07 | Open |
| 20 | Morag H | Arrange meeting to discuss pipelines and quick look tools. Personnel: Betty S, Jill B, Grant W, Morag H, Tim P, Roger Thompson | Early June | Open |
| 21 | Morag H | Verify access for MAESTRO team members on the MMT docuwiki - access created by Duane G and verified by Morag H - information passed to MAESTRO team. |  | Closed |
| 22 | Shawn C | Analyse rotator ring loading | Before 06/11/07 | Open |
| 23 | John G, Dennis S, Ken VH | Supply services in loading dock for MAESTRO use: vacuum pump, quiet power, internet connections (Cat V), LN2 (5 x 1 day supply), dry air, custom LN2 fill tube may be required. | Before 07/18/07 | Open |
| 24 | John G, Ken VH | Supply services in the pit – as loading dock plus power for clean room blower (does the floor need to be painted?) | Before 07/28/07 | Open |
| 25 | John G, Jill B, Ken VH | Produce acceptable cable drape plan | Before 07/24/07 | Open |
| 26 | Jill B | Review Ruby GUI software approach for spectrograph control with Skip S, Jeff R, Tim P, Grant W. | Before 07/01/07 | Open |
| 27 | Mike L | Rewrite CCD acquisition code to output a single fits file. | Before 07/01/07 | Open |
| 28 | Jill B | Develop workaround for displaying imagines after CCD code has been modified | Before 07/18/07 | Open |
| 29 | Mike L | Switch controllers and purchase PC to allow both SO guiders to be functional | Before 07/18/07 | Open |
| 30 | Jill B, Jeff R | Clarify how power to the Th Argon lamp in the on-board calibration box will be controlled. Inform John G of discussion. | Before 07/01/07 | Open |
| 31 | Morag H | Verify telescope operator for nights of 07/28/07 – 07/29/07 | Before 07/18/07 | Open |
| 32 | Russ W | Measure height of loading dock and distance of ‘flat’ section in front of dock at Tuscon. | Before ‘Delivery Meeting’ | Open |